## SUPERINTENDENT
MAJOR LAND DEVELOPMENT QA AND PRE PC CHECKLIST
H0123456 - Example Stage 9
SUPERINTENDENT:
Activity | Completion date | Signed | Date
Potable Water All works required have been completed and agreed with all stakeholders.
Hydrostatic test passed and documentation signed
Compaction test results
TS4 material certification
Weld certificates
Concrete dockets
Meter detail form completed
Water meters, tags, ties & backflows fitted to connections
Sewer All works required have been completed and agreed with all stakeholders.
Air test results
Man hole hydrostatic test results
CCTV report and acceptance report
Compaction test results
Screenings material certification
Concrete dockets submitted for MH bases (in-situ)
WWPS All works required have been completed and agreed with all stakeholders
Hydrostatic test for wet well and controlled MH passed
Factory Acceptance Testing
O&M manual
Asset in service audit completed
WHS walkover completed
40mm water service completed including certified RPZ
WWPS site accepted by SA Water Operations
Sewer Rising Main All works required have been completed and agreed with all stakeholders.
Hydrostatic test passed
Compaction test results
TS4 material certification
Weld certificates submitted for PE welds
Concrete dockets submitted for thrust blocks
Recycled Water All works have been completed and agreed with all stakeholders.
Hydrostatic test passed
Cross connection check completed
Compaction test results submitted
TS4 material certification submitted
Weld certificates submitted for PE welds
Concrete dockets submitted for thrust blocks
Meter detail form completed, submitted
Water meters, tags & ties supplied and fitted to connections
General
All ITP's have been completed and signed in relevant catagories, submitted
As Constructed ASCONS submitted to Reticulation Networks
Pre PC Walkover
SID 3 close out

## QA Checklist
MAJOR LAND DEVELOPMENT QUALITY ASSURANCE DOCUMENTATION REQUIREMENTS LIST
CAMS NUMBER: | STAGE NAME:
CONTRACTOR:
SUPERINTENDENT:
QUALITY ASSURANCE DOCUMENTATION REQUIREMENTS CHECKLIST
POTABLE WATER | REQUIRED | CONTRACTOR | SUBMITTED | DATE | SUPERINTENDENT | ENDORSED | DATE | SA WATER | ACCEPTED | DATE
Hydrostatic test records
Compaction test records
TS0631 material certfication
Poly Ethylene weld certficates
Concrete dockets
Water meter allocation form completed
RECYCLED WATER | REQUIRED | CONTRACTOR | SUBMITTED | DATE | SUPERINTENDENT | ENDORSED | DATE | SA WATER | ACCEPTED | DATE
Hydrostatic test records
Cross connection test records
Compaction test records
TS0631 material certfication
Poly Ethylene weld certficates
Concrete dockets
Water meter allocation form completed
GRAVITY SEWER | REQUIRED | CONTRACTOR | SUBMITTED | DATE | SUPERINTENDENT | ENDORSED | DATE | SA WATER | ACCEPTED | DATE
Air test / Vaccum test records
Maintenance Hole hydrostatic test records
CCTV Wincam, Video & Acceptance test report
Compaction test records
TS0630 material certification
Concrete dockets
SEWER RISING MAIN | REQUIRED | CONTRACTOR | SUBMITTED | DATE | SUPERINTENDENT | ENDORSED | DATE | SA WATER | ACCEPTED | DATE
Hydrostatic test records
Compaction test records
TS0631 material certification
Poly Ethylene weld certificates
Concrete dockets
WASTEWATER PUMP STATION | REQUIRED | CONTRACTOR | SUBMITTED | DATE | SUPERINTENDENT | ENDORSED | DATE | SA WATER | ACCEPTED | DATE
Wet well concrete certificates
Wet well / Control MH hyrdostatic test records
Compaction test records
TS0630 material certfication
Poly Ethlene weld certificates
Stainless steel pipework weld certificates
Switchboard Factory Acceptance Test records
Switchboard Site Acceptance Test records
Training records
Operation and maintenance manaual
Maximo asset data file
Signed label schedule
Backflow prevention device test record
Plumbing certificate of compliance
Electrical certificate of compliance
GENERAL | REQUIRED | CONTRACTOR | SUBMITTED | DATE | SUPERINTENDENT | ENDORSED | DATE | SA WATER | ACCEPTED | DATE
Safety in Design 3
Inspection Test Plans
As Constructed Drawings
Check Box 56
Check Box 57